AZURE DEVOPS

EPIC FEATURE DELIVERY TRACKER

Step-by-Step Power BI Build Guide

| Rolling Average Forecast | xViz Gantt Chart | Python KPI Visual |
| --- | --- | --- |

Data Source: Azure DevOps OData API

Forecast Method: 8-Week Rolling Average Throughput

Visuals: xViz Gantt + Python KPI + Native Cards

Audience: Stakeholders & Delivery Teams

# Table of Contents

# 1. Overview & Architecture

This guide walks you through building a complete stakeholder-ready Power BI report that tracks Epic and Feature delivery progress against target dates. The forecast is calculated using a rolling 8-week average throughput of T1 stories.

## What You Will Build

| Report Page | Visual | Purpose |
| --- | --- | --- |
| Delivery Tracker | Filter Bar (3 slicers) | Epic, Target Date range, Status filter |
| Delivery Tracker | KPI Cards (5) | On Track / At Risk / High Risk counts + avg % |
| Delivery Tracker | Python Bar Chart | Monthly throughput with rolling avg reference line |
| Delivery Tracker | xViz Gantt Chart | Feature bars, progress fill, forecast diamond |
| Delivery Tracker | Matrix Detail Table | Story counts, dates, buffer, status badges |

## Data Model

| Table | Key Fields | Role |
| --- | --- | --- |
| Epic | WorkItemId, Title | Parent grouping level |
| Feature | WorkItemId, EpicId, Title, TargetDate | Unit of delivery being tracked |
| UserStory | WorkItemId, FeatureId, State, ClosedDate, InProgressDate, Title | Stories that power throughput & progress |
| Date | Date, Month, Year, WeekNum | Time dimension for monthly KPI chart |

| ℹ NOTE | Relationships: Epic[WorkItemId] → Feature[EpicId] (1 to many). Feature[WorkItemId] → UserStory[FeatureId] (1 to many). Date[Date] → UserStory[ClosedDate] (1 to many). All cross-filter direction: Both. |
| --- | --- |

## Rolling Average — How It Works

The forecast uses the last N weeks (default: 8) of T1 story closures across the whole team to calculate a weekly average throughput. This is then used to project when remaining stories on each feature will complete.

| Formula | Value |
| --- | --- |
| Rolling Window | Last 8 weeks (56 days) — adjustable |
| T1 Filter | UserStory[Title] starts with "T1" |
| Weekly Throughput | T1 stories closed in window ÷ 8 |
| Weeks to Complete | Remaining stories ÷ Weekly Throughput |
| Forecast Date | TODAY() + (Weeks to Complete × 7) |
| On Track | Forecast Date ≤ Target Date − 14 days |
| At Risk | Forecast Date within 14 days of Target |
| High Risk | Forecast Date > Target Date |

# 2. Prerequisites

## Software Required

- Power BI Desktop — latest version (free download from Microsoft)

- Python 3.8+ with pip — for the KPI visual

- Python libraries: matplotlib, pandas, numpy

- xViz Gantt Chart visual — free from AppSource (Pro tier recommended for conditional bar color)

| 💡 TIP | To install Python libraries: open a terminal and run: pip install matplotlib pandas numpy |
| --- | --- |

## Azure DevOps Permissions

- You need Analytics View access on your Azure DevOps organisation

- The OData endpoint format is:  https://analytics.dev.azure.com/{org}/{project}/_odata/v4.0-preview/WorkItems

- Replace {org} and {project} with your organisation and project names

## Enable Python in Power BI

- Open Power BI Desktop

- Go to File → Options and Settings → Options

- Click Python scripting in the left panel

- Set Detected Python home directories to your Python installation path

- Click OK

| ⚠ WARNING | Power BI runs Python visuals in a restricted sandbox. Each time the report is refreshed or a slicer is changed, the Python script re-runs. Keep the script efficient — avoid loading files from disk inside the script. |
| --- | --- |

# 3. Connect to Azure DevOps OData

| STEP 3.1 | Open Power Query Editor |
| --- | --- |

- Open Power BI Desktop and click Get Data on the Home ribbon

- Search for OData feed and click Connect

- Enter your organisation URL:

https://analytics.dev.azure.com/{YOUR_ORG}/{YOUR_PROJECT}/_odata/v4.0-preview/WorkItems

- Click OK — Power BI will prompt for credentials

- Select Organisational account and sign in with your Azure DevOps credentials

- Click Connect to open the Navigator

| STEP 3.2 | Load the Epics Query |
| --- | --- |

In the Navigator window, do not select a table. Instead, click Transform Data to open Power Query. Then create three separate queries using Advanced Editor.

- In Power Query Editor, click New Source → Blank Query

- Right-click the new query and rename it Epics

- Click Advanced Editor and paste this M code:

let

Source = OData.Feed(

"https://analytics.dev.azure.com/{ORG}/{PROJECT}/_odata/v4.0-preview/WorkItems"

& "?$filter=WorkItemType eq 'Epic'"

& "&$select=WorkItemId,Title,State,AreaPath",

null, [Implementation="2.0"]

),

#"Filtered Rows" = Table.SelectRows(Source, each [WorkItemType] = "Epic")

in

#"Filtered Rows"

- Click Done

| 💡 TIP | If you get a firewall/permission error, click Edit Credentials in the yellow banner and re-authenticate with Organisational Account. |
| --- | --- |

| STEP 3.3 | Load the Features Query |
| --- | --- |

- Click New Source → Blank Query, rename it Features

- Open Advanced Editor and paste:

let

Source = OData.Feed(

"https://analytics.dev.azure.com/{ORG}/{PROJECT}/_odata/v4.0-preview/WorkItems"

& "?$filter=WorkItemType eq 'Feature'"

& "&$select=WorkItemId,Title,State,TargetDate,ParentWorkItemId",

null, [Implementation="2.0"]

),

#"Filtered Rows" = Table.SelectRows(Source, each [WorkItemType] = "Feature"),

#"Renamed Columns" = Table.RenameColumns(

#"Filtered Rows",

{{"ParentWorkItemId", "EpicId"}}

)

in

#"Renamed Columns"

| ℹ NOTE | ParentWorkItemId on a Feature is its parent Epic's WorkItemId. Renaming it to EpicId makes the relationship clearer and matches the DAX measure names. |
| --- | --- |

| STEP 3.4 | Load the User Stories Query |
| --- | --- |

- Create another blank query, rename it UserStories

- Open Advanced Editor and paste:

let

Source = OData.Feed(

"https://analytics.dev.azure.com/{ORG}/{PROJECT}/_odata/v4.0-preview/WorkItems"

& "?$filter=WorkItemType eq 'User Story'"

& "&$select=WorkItemId,Title,State,ClosedDate,ActivatedDate,ParentWorkItemId",

null, [Implementation="2.0"]

),

#"Filtered Rows" = Table.SelectRows(Source, each [WorkItemType] = "User Story"),

#"Renamed Columns" = Table.RenameColumns(

#"Filtered Rows",

{{"ParentWorkItemId", "FeatureId"}, {"ActivatedDate", "InProgressDate"}}

)

in

#"Renamed Columns"

| STEP 3.5 | Create the Date Dimension Table |
| --- | --- |

- Click New Source → Blank Query, rename it Date

- Open Advanced Editor and paste:

let

StartDate = #date(2024, 1, 1),

EndDate   = Date.From(DateTime.LocalNow()),

DateList  = List.Dates(StartDate, Duration.Days(EndDate - StartDate) + 365, #duration(1,0,0,0)),

#"To Table" = Table.FromList(DateList, Splitter.SplitByNothing(), {"Date"}),

#"Changed Type" = Table.TransformColumnTypes(#"To Table", {{"Date", type date}}),

#"Added Month" = Table.AddColumn(#"Changed Type", "MonthYear",

each Date.ToText([Date], "MMM yyyy"), type text),

#"Added WeekNum" = Table.AddColumn(#"Added Month", "WeekNum",

each Date.WeekOfYear([Date]), type number),

#"Added Year" = Table.AddColumn(#"Added WeekNum", "Year",

each Date.Year([Date]), type number)

in

#"Added Year"

- Click Done, then click Close & Apply on the Home ribbon

| ✓ RESULT | You now have 4 tables loaded: Epics, Features, UserStories, Date. The status bar at the bottom of Power BI will show the row counts as data loads. |
| --- | --- |

# 4. Build the Data Model

| STEP 4.1 | Switch to Model View |
| --- | --- |

- Click the Model view icon in the left sidebar (looks like 3 connected boxes)

- You will see your 4 tables laid out — rearrange them so:

  - Epics is top-left

  - Features is top-right

  - UserStories is bottom-center

  - Date is bottom-right

| STEP 4.2 | Create Relationships |
| --- | --- |

Create each relationship by dragging from the source column to the target column:

| From Table → Column | To Table → Column | Cardinality | Cross-filter |
| --- | --- | --- | --- |
| Epic → WorkItemId | Feature → EpicId | One to Many (1:*) | Both |
| Feature → WorkItemId | UserStory → FeatureId | One to Many (1:*) | Both |
| Date → Date | UserStory → ClosedDate | One to Many (1:*) | Single |

For each relationship:

- Drag the column from the "From" table and drop onto the "To" column

- Double-click the relationship line that appears

- In the Edit relationship dialog, verify Cardinality and set Cross filter direction

- Click OK

| ⚠ WARNING | If Power BI creates a Many-to-Many relationship instead of One-to-Many, it means there are duplicate WorkItemId values in the Epics or Features table. Go back to Power Query and add a Remove Duplicates step on the WorkItemId column. |
| --- | --- |

| STEP 4.3 | Mark the Date Table |
| --- | --- |

- Click the Date table in Model view to select it

- Go to Table tools ribbon at the top

- Click Mark as date table

- Select Date as the date column

- Click OK

| 💡 TIP | Marking the Date table unlocks time intelligence functions like DATESINPERIOD which is needed for the rolling average measures. |
| --- | --- |

# 5. Create DAX Measures

All measures go into the Features table unless otherwise noted. Right-click Features → New measure for each one.

| 💡 TIP | Create a dedicated Measures table: Home ribbon → Enter Data → create a blank table called _Measures. Put all measures there to keep the model clean. The table can have a single dummy column you never use. |
| --- | --- |

| STEP 5.1 | Story Count Measures |
| --- | --- |

### Total Stories

Total Stories =

COUNTROWS(UserStory)

### Closed Stories

Closed Stories =

CALCULATE(

COUNTROWS(UserStory),

UserStory[State] IN {"Closed", "Done", "Resolved"}

)

### Remaining Stories

Remaining Stories =

[Total Stories] - [Closed Stories]

### InProgress Stories

InProgress Stories =

CALCULATE(

COUNTROWS(UserStory),

UserStory[State] IN {"Active", "In Progress", "Committed"}

)

### Feature Pct Complete

Feature Pct Complete =

DIVIDE([Closed Stories], [Total Stories], 0) * 100

| STEP 5.2 | Feature Date Measures |
| --- | --- |

### Feature Start Date

Feature Start Date =

CALCULATE(

MIN(UserStory[InProgressDate]),

NOT ISBLANK(UserStory[InProgressDate])

)

### Feature Target Date

Feature Target Date =

MAX(Feature[TargetDate])

| ℹ NOTE | Feature Start Date is the date the first User Story under this feature moved to In Progress. This is used as the left edge of the Gantt bar. |
| --- | --- |

| STEP 5.3 | Rolling Average Throughput (Core Forecast Engine) |
| --- | --- |

This is the key measure. It counts T1 stories closed in the last 8 weeks, team-wide, then divides by 8 to get a weekly rate. The ALL(Feature) removes any Epic or Feature slicer context so throughput is always team-wide.

### Rolling Window Weeks  (tune this to change the window)

Rolling Window Weeks = 8

// Change to 4 for more reactive (recent-focused)

// Change to 12 for more stable (smoothed over 3 months)

### Rolling Avg Weekly Throughput

Rolling Avg Weekly Throughput =

VAR _n     = [Rolling Window Weeks]

VAR _days  = _n * 7

VAR _count =

CALCULATE(

COUNTROWS(UserStory),

ALL(Feature),              // team-wide: ignore Epic slicer

ALL(Epic),

UserStory[State] IN {"Closed","Done","Resolved"},

LEFT(TRIM(UserStory[Title]), 2) = "T1",

NOT ISBLANK(UserStory[ClosedDate]),

UserStory[ClosedDate] >= TODAY() - _days,

UserStory[ClosedDate] <= TODAY()

)

RETURN

DIVIDE(_count, _n, 0)  // stories per week

| STEP 5.4 | Forecast Date |
| --- | --- |

Forecast Date =

VAR _throughput = [Rolling Avg Weekly Throughput]

VAR _remaining  = [Remaining Stories]

VAR _weeks      = DIVIDE(_remaining, _throughput, 999)

VAR _days       = ROUND(_weeks * 7, 0)

RETURN

IF(

_throughput > 0 && NOT ISBLANK(_throughput),

TODAY() + _days,

BLANK()

)

| ℹ NOTE | If throughput is 0 (no T1 stories closed in the window), the measure returns BLANK rather than infinity. Features with BLANK forecasts will show as "No Data" in the status measure. |
| --- | --- |

| STEP 5.5 | Status & Buffer |
| --- | --- |

### Forecast Buffer Days

Forecast Buffer Days =

VAR _target   = [Feature Target Date]

VAR _forecast = [Forecast Date]

RETURN

IF(

NOT ISBLANK(_forecast) && NOT ISBLANK(_target),

DATEDIFF(_forecast, _target, DAY),

BLANK()

)

### Feature Status

Feature Status =

VAR _buf      = [Forecast Buffer Days]

VAR _pct      = [Feature Pct Complete] / 100

VAR _start    = [Feature Start Date]

VAR _target   = [Feature Target Date]

VAR _elapsed  = DIVIDE(DATEDIFF(_start, TODAY(), DAY),

DATEDIFF(_start, _target, DAY), 0)

VAR _pace_gap = _elapsed - _pct   // positive = behind pace

RETURN

SWITCH(TRUE(),

ISBLANK(_buf),     "No Data",

_buf < 0,          "High Risk",

_buf < 14,         "At Risk",

_pace_gap > 0.20,  "At Risk",

_pct = 1,          "Complete",

"On Track"

)

### Status Color  (for conditional formatting)

Status Color =

SWITCH([Feature Status],

"On Track",  "#00D68F",

"At Risk",   "#FFAA00",

"High Risk", "#FF4D6A",

"Complete",  "#60A5FA",

"#7FA8C9"

)

| STEP 5.6 | KPI Count Measures (for the card visuals) |
| --- | --- |

Count On Track =

CALCULATE(

DISTINCTCOUNT(Feature[WorkItemId]),

[Feature Status] = "On Track"

)

Count At Risk =

CALCULATE(

DISTINCTCOUNT(Feature[WorkItemId]),

[Feature Status] = "At Risk"

)

Count High Risk =

CALCULATE(

DISTINCTCOUNT(Feature[WorkItemId]),

[Feature Status] = "High Risk"

)

Avg Pct Complete =

AVERAGEX(Feature, [Feature Pct Complete])

| STEP 5.7 | Monthly Throughput (for KPI bar chart) |
| --- | --- |

Monthly T1 Closed =

CALCULATE(

COUNTROWS(UserStory),

UserStory[State] IN {"Closed","Done","Resolved"},

LEFT(TRIM(UserStory[Title]), 2) = "T1"

)

// Place this on a Column chart with Date[MonthYear] as X axis

// Add a constant line using [Rolling Avg Weekly Throughput] * 4.33

// to show the monthly equivalent of the rolling average

Monthly Avg Reference =

[Rolling Avg Weekly Throughput] * 4.33  // weeks per month

| ℹ NOTE | 4.33 is the average number of weeks per month (52 weeks ÷ 12 months). Multiplying the weekly throughput by 4.33 converts it to a monthly equivalent for the bar chart reference line. |
| --- | --- |

# 6. Page Layout & Canvas Setup

| STEP 6.1 | Set Canvas Size |
| --- | --- |

- In Report view, click on a blank area of the canvas

- In the Visualizations pane on the right, click the Format your report page icon (paint roller)

- Expand Canvas settings

- Set Type to Custom

- Set Width to 1920 and Height to 1080

- Set Background to a custom color: #0D1B2A (dark navy)

| 💡 TIP | Setting a dark background makes the report feel premium and matches the Python visual theme. All text and card backgrounds will need light colors to remain readable. |
| --- | --- |

| STEP 6.2 | Page Layout Grid |
| --- | --- |

The page is divided into 4 horizontal zones. Use these pixel coordinates as guides:

| Zone | Y Start | Height | Contents |
| --- | --- | --- | --- |
| Title Bar | 0 | 60 | Page title text box |
| Filter Bar | 60 | 70 | 3 Slicers side by side |
| KPI + Chart | 130 | 180 | 5 KPI cards + Python throughput bar |
| Gantt Chart | 310 | 540 | xViz Gantt visual |
| Detail Table | 850 | 230 | Matrix table with story details |

| STEP 6.3 | Add Title Text Box |
| --- | --- |

- Click Insert → Text box on the ribbon

- Draw it across the top of the canvas (full width, ~60px tall)

- Type: EPIC FEATURE DELIVERY TRACKER

- Select all text → set Font to Segoe UI, Size 20, Bold, Color white (#FFFFFF)

- In Format pane → Background → set fill color to #112236

- Add a second line of smaller text: As of [today] · Forecast: 8-Week Rolling Average · T1 Stories

# 7. Add Slicers (Filter Bar)

| STEP 7.1 | Epic Title Dropdown Slicer |
| --- | --- |

- Click the Slicer visual icon in the Visualizations pane

- Draw it in the Filter Bar zone — left third of the bar

- Drag Epic[Title] into the Field well

- In the Format pane → Slicer settings → Style: Dropdown

- Set Header text to: Select Epic

- Format → Background: #112236, Border: none

- Format → Values → Font color: #E8F4FD, Background: #0D1B2A

| STEP 7.2 | Target Date Range Slicer |
| --- | --- |

- Add another Slicer visual in the middle third of the Filter Bar

- Drag Feature[TargetDate] into the Field well

- Format → Slicer settings → Style: Between (date range)

- Set Header text to: Target Date Range

- Apply same dark background formatting as Step 7.1

| STEP 7.3 | Status Slicer |
| --- | --- |

This slicer filters by Feature Status. Because Status is a measure (not a column), you need to create a disconnected table first.

- On the Home ribbon, click Enter Data

- Create a table with one column called Status and four rows:

  - On Track

  - At Risk

  - High Risk

  - Complete

- Name the table StatusFilter and click Load

- Do NOT create a relationship between StatusFilter and any other table

- Add a Slicer visual in the right third of the Filter Bar

- Drag StatusFilter[Status] into the Field well

- Format → Slicer settings → Style: Tile

Now connect the slicer to visuals using a measure:

Is Selected Status =

VAR _sel = SELECTEDVALUE(StatusFilter[Status], "All")

RETURN

IF(

_sel = "All",

TRUE(),

[Feature Status] = _sel

)

Add this measure as a Visual level filter (= TRUE) on the xViz Gantt and the Matrix table.

# 8. Add KPI Cards

Place 5 cards in the left portion of the KPI zone, stacked or side-by-side.

| STEP 8.1 | Add Each Card |
| --- | --- |

Repeat this process for each card:

- Click the Card visual icon in the Visualizations pane

- Draw a small box in the KPI zone

- Drag the measure into the Fields well

| Card # | Measure | Title | Color |
| --- | --- | --- | --- |
| 1 | [Count On Track] | On Track | #00D68F |
| 2 | [Count At Risk] | At Risk | #FFAA00 |
| 3 | [Count High Risk] | High Risk | #FF4D6A |
| 4 | [Avg Pct Complete] | Avg Complete | #60A5FA |
| 5 | [Rolling Avg Weekly Throughput] | Stories/Week | #A78BFA |

| STEP 8.2 | Format Each Card |
| --- | --- |

- Select the card, open Format pane

- Background: #112236, Border: none, Shadow: off

- Callout value → Font: Segoe UI, Size 28, Bold

- Set font color to the color shown in the table above for each card

- Category label → text = the title from the table above

- Category label → Font color: #7FA8C9 (muted blue-grey)

| 💡 TIP | Hold Ctrl and click all 5 cards, then use Format → Align → Distribute horizontally to space them evenly. |
| --- | --- |

# 9. Python Monthly Throughput Chart

| STEP 9.1 | Add the Python Visual |
| --- | --- |

- In the Visualizations pane, click the Python visual icon (Py)

- Draw it in the right portion of the KPI zone (about 60% of the width)

- A yellow banner will appear asking to enable Python visuals — click Enable

| STEP 9.2 | Add Fields to the Visual |
| --- | --- |

Drag these fields into the Values well of the Python visual:

- Date[MonthYear]  — this groups data by month

- [Monthly T1 Closed]  — story count per month

- [Monthly Avg Reference]  — the rolling average line value

| ℹ NOTE | Power BI will automatically pass these as columns in a pandas DataFrame called dataset. The column names will match the field names you drag in. |
| --- | --- |

| STEP 9.3 | Paste the Python Script |
| --- | --- |

In the Python script editor panel at the bottom of the screen, delete the placeholder text and paste the following script. This creates the dark-themed bar chart with the rolling average reference line.

import matplotlib

matplotlib.use("Agg")

import matplotlib.pyplot as plt

import matplotlib.patheffects as pe

import pandas as pd

import numpy as np

import warnings

warnings.filterwarnings("ignore")

# Power BI provides `dataset` automatically

df = dataset.copy()

THEME = {

"bg":    "#0D1B2A",

"panel": "#112236",

"text":  "#E8F4FD",

"dim":   "#7FA8C9",

"grid":  "#1A3050",

"bar":   "#1E6FD9",

"ref":   "#A78BFA",

}

plt.rcParams.update({

"font.family": "DejaVu Sans",

"figure.facecolor": THEME["bg"],

"axes.facecolor": THEME["panel"],

"axes.edgecolor": THEME["grid"],

"text.color": THEME["text"],

"xtick.color": THEME["dim"],

"ytick.color": THEME["dim"],

})

fig, ax = plt.subplots(figsize=(14, 4))

fig.subplots_adjust(left=0.06, right=0.97, top=0.80, bottom=0.22)

x = np.arange(len(df))

bars = ax.bar(x, df["Monthly T1 Closed"], color=THEME["bar"],

width=0.65, edgecolor=THEME["bg"], linewidth=0.6)

# Value labels on bars

for bar, val in zip(bars, df["Monthly T1 Closed"]):

ax.text(bar.get_x() + bar.get_width()/2, bar.get_height() + 0.1,

str(int(val)), ha="center", va="bottom", fontsize=8,

fontweight="bold", color=THEME["text"])

# Rolling average reference line

avg_val = df["Monthly Avg Reference"].mean()

ax.axhline(avg_val, color=THEME["ref"], linewidth=2, linestyle="--")

ax.text(len(df) - 0.4, avg_val + 0.15,

f"Avg: {avg_val:.1f}", ha="right", va="bottom",

fontsize=8, fontweight="bold", color=THEME["ref"])

ax.set_xticks(x)

ax.set_xticklabels(df["MonthYear"], rotation=30, ha="right", fontsize=8)

ax.set_ylim(0, df["Monthly T1 Closed"].max() * 1.3)

ax.set_title("Monthly T1 Story Throughput  ·  Last 12 Months",

fontsize=10, fontweight="bold", color=THEME["text"], pad=8)

ax.grid(axis="y", color=THEME["grid"], linewidth=0.5, alpha=0.6)

ax.set_axisbelow(True)

for spine in ["top", "right"]:

ax.spines[spine].set_visible(False)

plt.show()

- Click the Run button (triangle) to execute the script

| ✓ RESULT | A dark bar chart appears showing stories closed per month with the rolling average as a purple dashed reference line. If you see an error, check that matplotlib, pandas and numpy are installed in the Python environment Power BI is pointing to. |
| --- | --- |

# 10. xViz Gantt Chart

| STEP 10.1 | Install xViz from AppSource |
| --- | --- |

- Click the three dots (...) at the bottom of the Visualizations pane

- Select Get more visuals

- In the AppSource dialog, search for: xViz Gantt Chart

- Click Add on the xViz Gantt Chart by xViz

- The icon will now appear in your Visualizations pane

| STEP 10.2 | Draw and Size the Gantt |
| --- | --- |

- Click the xViz Gantt icon in the Visualizations pane

- Draw the visual to fill the Gantt zone (full width, ~540px tall)

- In the Format pane, set the visual background to #0D1B2A

| STEP 10.3 | Map Fields to the Gantt |
| --- | --- |

Drag fields into the xViz field wells in the order shown:

| xViz Field Well | What to Drag In | Source |
| --- | --- | --- |
| Category (Row label) | Title | Feature table |
| Parent (Grouping) | Title | Epic table — this creates collapsible epic headers |
| Start Date | Feature Start Date | Measure |
| End Date | TargetDate | Feature table column |
| Milestone 1 | Forecast Date | Measure |
| Progress % | Feature Pct Complete | Measure |
| Tooltip | Feature Status | Measure |
| Tooltip | Forecast Buffer Days | Measure |
| Tooltip | Closed Stories | Measure |
| Tooltip | Total Stories | Measure |

| STEP 10.4 | Format the Gantt — General |
| --- | --- |

Open the Format pane for the Gantt visual. Work through each section:

| Background color | #0D1B2A |
| --- | --- |

| Font family | Segoe UI |
| --- | --- |

| Font color (rows) | #E8F4FD |
| --- | --- |

| Grid color | #1A3050 |
| --- | --- |

| Row height | 44 px |
| --- | --- |

| STEP 10.5 | Format — Today Line |
| --- | --- |

| Show today line | On |
| --- | --- |

| Today line color | #FFFFFF |
| --- | --- |

| Today line width | 2 px |
| --- | --- |

| Show today label | On |
| --- | --- |

| Today label text | TODAY |
| --- | --- |

| STEP 10.6 | Format — Gantt Bars |
| --- | --- |

| Bar background (planned) | #162B40 |
| --- | --- |

| Bar border color | #1E3A55 |
| --- | --- |

| Bar border size | 1 px |
| --- | --- |

| Show progress bar | On |
| --- | --- |

| Progress bar height | 65% of bar |
| --- | --- |

For the progress bar color, use Conditional Formatting:

- Click the progress bar color field

- Toggle Conditional formatting ON

- Select Rules and add the following rules in order:

  - If "Feature Status" equals "High Risk" → color = #FF4D6A

  - If "Feature Status" equals "At Risk" → color = #FFAA00

  - If "Feature Status" equals "On Track" → color = #00D68F

  - If "Feature Status" equals "Complete" → color = #60A5FA

- Set the default color (no rules match) to #1E6FD9

| STEP 10.7 | Format — Milestone (Forecast Date) |
| --- | --- |

| Milestone 1 shape | Diamond ◆ |
| --- | --- |

| Milestone 1 color | #A78BFA |
| --- | --- |

| Milestone 1 size | 12 px |
| --- | --- |

| Show milestone label | On |
| --- | --- |

| Milestone label position | Above bar |
| --- | --- |

| Milestone label format | DD MMM |
| --- | --- |

| STEP 10.8 | Format — Group Headers (Epic rows) |
| --- | --- |

| Group header background | #0A2540 |
| --- | --- |

| Group header font | Bold, 11pt, #E8F4FD |
| --- | --- |

| Show expand/collapse icon | On |
| --- | --- |

| Left accent bar | #1E6FD9 — if available in your xViz version |
| --- | --- |

| STEP 10.9 | Format — Data Columns (right of bar label) |
| --- | --- |

xViz allows adding static info columns beside the task label. Add these:

| Column # | Measure | Header | Width | Format |
| --- | --- | --- | --- | --- |
| 1 | Feature Pct Complete | % | 60px | 0"%" |
| 2 | Closed Stories | Done | 50px | whole number |
| 3 | Total Stories | Total | 50px | whole number |
| 4 | Feature Target Date | Target | 70px | DD MMM |
| 5 | Forecast Buffer Days | Buffer | 60px | +0;-0;" d" |

Apply conditional formatting to the Buffer column:

  - Less than 0 → font color #FF4D6A (red)

  - 0 to 13 → font color #FFAA00 (amber)

  - 14 or more → font color #00D68F (green)

| STEP 10.10 | Add Visual Level Filter for Status Slicer |
| --- | --- |

- Select the xViz Gantt visual

- In the Filters pane on the right, expand Filters on this visual

- Drag the [Is Selected Status] measure into this area

- Set the filter condition to: is True

- Click Apply filter

| ✓ RESULT | The Gantt now responds to the Status slicer. Selecting "At Risk" collapses all On Track and High Risk rows, leaving only At Risk features visible. |
| --- | --- |

# 11. Detail Matrix Table

| STEP 11.1 | Add the Matrix Visual |
| --- | --- |

- Click the Matrix visual icon in the Visualizations pane

- Draw it to fill the Detail Table zone at the bottom of the canvas

| STEP 11.2 | Configure Matrix Fields |
| --- | --- |

| Well | Field / Measure | Display Name |
| --- | --- | --- |
| Rows | Epic[Title] | Epic |
| Rows | Feature[Title] | Feature |
| Values | [Feature Start Date] | Started |
| Values | Feature[TargetDate] | Target |
| Values | [Forecast Date] | Forecast |
| Values | [Forecast Buffer Days] | Buffer (d) |
| Values | [Closed Stories] | Done |
| Values | [Total Stories] | Total |
| Values | [Feature Pct Complete] | % Done |
| Values | [Feature Status] | Status |

| STEP 11.3 | Format the Matrix |
| --- | --- |

- Format pane → Background: #112236

- Grid → Horizontal grid lines: on, color #1A3050

- Values → Font size: 9, Font color: #E8F4FD

- Column headers → Bold, background #0A2540, font #7FA8C9

- Row headers → Font: #E8F4FD, Epic rows bold

### Conditional Formatting on Status column:

- Select the matrix → Values → Status column → right-click → Conditional formatting → Background color

- Set Format by: Field value

- Select the [Status Color] measure

- Click OK

### Conditional Formatting on % Done column:

- Right-click the % Done column → Conditional formatting → Data bars

- Set Minimum to 0, Maximum to 100

- Positive bar color: #1E6FD9

- Click OK

### Conditional Formatting on Buffer column:

- Right-click Buffer → Conditional formatting → Font color

- Select Rules

  - If value is less than 0 → color #FF4D6A

  - If value is between 0 and 13 → color #FFAA00

  - If value is 14 or more → color #00D68F

- Click OK

# 12. Configure Slicer Interactions

| STEP 12.1 | Verify Default Interactions |
| --- | --- |

By default, Power BI slicers filter all visuals on the page. Verify this:

- Click the Epic slicer

- On the Format ribbon, click Edit interactions

- You will see filter icons appear on all other visuals

- Each visual should show the funnel icon (filter) not the slash icon (no interaction)

- If any visual shows the slash, click the funnel icon above it to enable filtering

- Click Edit interactions again to exit

| STEP 12.2 | Test the Report |
| --- | --- |

- Select an Epic in the dropdown slicer

- Verify the Gantt shows only features for that Epic, grouped under the Epic header

- Select a date range — features whose Target Date falls outside the range should disappear

- Click High Risk in the Status slicer — only High Risk features should remain

- Click the Epic slicer clear button (X) to reset and show all Epics

| 💡 TIP | If the Python chart is not filtering with the slicers, check that Date[MonthYear] in its field well is linked to the UserStory[ClosedDate] via the Date table relationship — not as a disconnected field. |
| --- | --- |

# 13. Tuning & Maintenance

## Changing the Rolling Window

The Rolling Window Weeks measure controls how many weeks of history are used. To change it:

- Go to the Data view (table icon in left sidebar)

- Click the _Measures table

- Click the Rolling Window Weeks measure in the field list

- Change the value from 8 to your desired number in the formula bar

- Press Enter

| Window | Weeks | Best For |
| --- | --- | --- |
| Reactive | 4 | Fast-changing teams or new processes. High variance. |
| Balanced | 8 | Most teams on monthly planning cycles. Recommended. |
| Stable | 12 | Mature teams with very consistent output. |
| Historical | 26 | Equivalent to the 6-month percentile approach. |

## Status Thresholds

The 14-day buffer threshold and 20% pace gap threshold in the Feature Status measure can be tuned to your team's risk appetite:

// In the Feature Status measure:

_buf < 14    →  change 14 to a higher number for earlier At Risk warnings

_pace_gap > 0.20  →  change 0.20 to 0.10 for more sensitive pace detection

## Refreshing the Data

- Click Refresh on the Home ribbon to pull latest data from Azure DevOps

- All measures recalculate automatically against the refreshed data

- For scheduled refresh, publish to Power BI Service and set a gateway connection

| ℹ NOTE | The OData feed requires authentication each time. In Power BI Service, configure a gateway with your Azure DevOps credentials stored securely. |
| --- | --- |

# 14. Quick Reference

## All Measures — Summary

| Measure Name | Returns | Used In |
| --- | --- | --- |
| Total Stories | Count of all stories | Detail table |
| Closed Stories | Count of Closed/Done/Resolved | Gantt, table, KPI |
| Remaining Stories | Total - Closed | Forecast calc |
| InProgress Stories | Count of Active/In Progress | Table tooltip |
| Feature Pct Complete | 0-100 percentage | Gantt progress bar |
| Feature Start Date | Min InProgressDate of child stories | Gantt start |
| Feature Target Date | MAX of Feature[TargetDate] | Gantt end |
| Rolling Window Weeks | Constant (default: 8) | Throughput calc |
| Rolling Avg Weekly Throughput | Stories/week over window | KPI card, forecast |
| Forecast Date | Date when remaining stories finish | Gantt milestone |
| Forecast Buffer Days | Days between forecast and target | Status, table |
| Feature Status | On Track / At Risk / High Risk | Gantt, cards, slicer |
| Status Color | Hex color string for formatting | Conditional format |
| Count On Track | Feature count by status | KPI card |
| Count At Risk | Feature count by status | KPI card |
| Count High Risk | Feature count by status | KPI card |
| Avg Pct Complete | Average across all features | KPI card |
| Monthly T1 Closed | Stories closed per month (chart) | Python visual |
| Monthly Avg Reference | Throughput converted to monthly | Python ref line |
| Is Selected Status | Boolean for status slicer filter | Visual filter |

## Troubleshooting

| Problem | Likely Cause | Fix |
| --- | --- | --- |
| Gantt shows blank start dates | Stories never moved to In Progress | Check InProgressDate column is mapped from ActivatedDate in Power Query |
| Forecast Date is blank | No T1 stories closed in rolling window | Check story titles start with "T1", check ClosedDate is populated |
| Status slicer does not filter Gantt | Is Selected Status not added as visual filter | Add measure as visual level filter = TRUE on Gantt |
| Throughput is too high | ALL() not applied — epic scope leaking in | Verify ALL(Feature) and ALL(Epic) are in the Rolling Avg measure |
| Python chart not showing | Wrong Python environment path | File → Options → Python scripting → verify path |
| Many-to-many relationship error | Duplicate WorkItemIds in Epics table | Power Query → Remove Duplicates on WorkItemId |
| OData slow or timing out | Too many rows without server-side filter | Add $top=5000 or a date filter to the OData URL in Power Query |